Meeting Minutes

Subject: Product feedback and Scale-up Lab Activities

Date: Monday, May 27, 2019

Location: Green Elec Lab

- Attendance

| No. | Name | Position | Organization |
| --- | --- | --- | --- |
| 1 | Quentin Merand | Education Institute | SE France |
| 2 | Phong DUONG Vu | CSR & Edu Delegate | SE VN |
| 3 | Loan Kim | Project Manager | ASSIST |
| 4 | Đức Nguyễn Minh | Green Elec Lab Leader | LTT |
| 5 | Bảo | Head Elec. Dept. | LTT |
| 6 | Cường Nguyễn Minh Đức | Lecture Elec. Dept. | LTT |

- Discussion

- Overall / Product feedback

- Solar water pump bench (MD3BPODS): two solar panel does not provide enough power for operation.

- Quentin checks the product with FR team.

- Communicate HMI – PLC via cable

- Quentin send these user guidelines / specifications to Mr.Duc – LTT College

- Motion control products to describe realistic movement, connect with PLC.

Already had PLC – HMI. Need speed controller, hardware part (Ox, Oy Axis)

Lexium 32 single phase servo-variable speed controller pack          MD1APLX32M

2-axis Cartesian robot with motors MD1APMTMAX2

- Solar system 3 phases: realistic / commercial products for student practicing.

- LTT college buys from another consumer.

- Scale-up Lab Activities

Not only continually training official students, but also focusing on Teachers, Workers.

Aims to design the Artificial Intelligence (AI), Smart Lab or partly of it.

Connected devices.

- Renewable Energy – Solar energy.

- Smart home – smart building.

- Mechatronic - pneumatic

- Scale up the training benches based on the beneficiaries’ quantity and studying time frame.

- Mr. Duc prepares the List of products needed for the Lab based on existing one.

- Smart home: page B14, E10

- Mechatronic: E69

C. Summary of next step

| No. | Task | PIC | Deadline |
| --- | --- | --- | --- |
| 1 | Solar water pump bench (MD3BPODS) check the power supply with 02 solar panels | Quentin | 15/08/2019 |
| 2 | guidelines / specifications: Communicate HMI – PLC via cable | Quentin | 15/08/2019 |
| 3 | List of products needed for the Lab based on existing one | Mr.Đức | 05/08/2019 |
| 4 | Proposing List of products need for purpose: - Renewable Energy – Solar energy. - Smart home – smart building. - Mechatronic – pneumatic - Also including: Lexium 32 single phase servo-variable speed controller pack MD1APLX32M 2-axis Cartesian robot with motors MD1APMTMAX2 Smart home: page B14, E10 Mechatronic: E69 | Quentin | 20/08/2019 |

-End-