## Master schedule 20170215
| Tháng | 2 |  | 3 |  |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  |  | 7 |  |  |  | 8 |  |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  |  | 12
| Tuần làm việc | t7 | t8 | t9 | t10 | t11 | t12 | t13 | t14 | t15 | t16 | t17 | t18 | t19 | t20 | t21 | t22 | t23 | t24 | t25 | t26 | t27 | t28 | t29 | t30 | t31 | t32 | t33 | t34 | t35 | t36 | t37 | t38 | t39 | t40 | t41 | t42 | t43 | t44 | t45 | t46 | t47 | t48 | t49 | t50 | t51 | t52
I | Xây dựng trung tâm huấn luyện
1 | Chuẩn bị và duyệt lại tài liệu đấu thầu | bar: 2 t7
2 | Đấu thầu | bar: 2 t8 to 3 t9
3 | Đánh giá đấu thầu và liên hệ nhân công | bar: 3 t10 to 3 t11
4 | Xin giấy phép xây dựng | bar: 3 t12 to 4 t15
5 | Giai đoạn xây dựng | bar: 4 t15 to 8 t33
6 | Lắp đặt thiết bị | bar: 8 t31 to 8 t35
7 | Hoàn tất xây dựng | bar: 9 t36 to 9 t37
8 | Đặt mua Thiết bị đào tạo | bar: 6 t22 to 8 t33
9 | Lắp đặt Thiết bị đào tạo | bar: 8 t34 to 9 t37
10 | Đặt mua Nội thất | bar: 7 t28 to 8 t35
11 | Trang trí Nội thất | bar: 9 t36 to 9 t37
12 | Kiểm tra, hoàn thiện khiếm khuyết và bàn giao | bar: 9 t38 to 9 t39
13 | Chuẩn bị và Khánh thành | bar: 10 t40
II | Điều hành Trung tâm Đào tạo
14 | Định hình khoá đào tạo | bar: 3 t9 to 3 t13
15 | Phát triển cấu trúc đào tạo | bar: 3 t11 to 4 t15
16 | Phát triển tài nguyên đào tạo | bar: 3 t11 to 9 t39
17 | Đào tạo cơ bản cho nhân viên
18 | Đào tạo Cài đặt (bao gồm nhà thầu) | bar: 4 t14 to 5 t20
Đào tạo Đội bảo trì | bar: 5 t21 to 7 t30
19 | Đào tạo Giám sát viên
20 | Đào tạo Kiểm tra viên
21 | Thực tập sinh ngoài và nhân viên mới của KVI
22 | Đào tạo Giảng viên | bar: 5 t18 to 7 t30
23 | Đào tạo Người mới và Học viên | bar: 8 t31 to 10 t43
24

## Sheet1 (2) (hidden)
| Month | Feb |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
| Working week | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | w15 | w16 | w17 | w18 | w19 | w20 | w21 | w22 | w23 | w24 | w25 | w26 | w27 | w28 | w29 | w30 | w31 | w32 | w33 | w34 | w35 | w36 | w37 | w38 | w39 | w40 | w41 | w42 | w43 | w44 | w45 | w46 | w47 | w48 | w49 | w50 | w51 | w52
1 | Bidding document preparation and review | bar: Feb w7
2 | Bidding | bar: Feb w8 to Mar w9
4 | Bidding evaluation and contacting works | bar: Mar w10 to Mar w11
5 | Construction permit approval | bar: Mar w12 to Apr w15
6 | Construction phase | bar: Apr w15 to Aug w33
7 | Facilities insatllation | bar: Aug w31 to Aug w35
8 | Building Finishing | bar: Sep w36 to Sep w37
9 | Training Equipment order | bar: Jun w22 to Aug w33
10 | Training Equipment installation | bar: Aug w34 to Sep w37
11 | Furniture order | bar: Jul w28 to Aug w35
12 | Funiture installation | bar: Sep w36 to Sep w37
13 | Full funtional testing defects fix and handover | bar: Sep w38 to Sep w39
14 | Preparation and Grand Opening | bar: Oct w40
Scope of KVI
Scope of Construction Contractor
Scope of Furniture Contractor

## Sheet1 (hidden)
Month | Feb |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
Working week | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | w15 | w16 | w17 | w18 | w19 | w20 | w21 | w22 | w23 | w24 | w25 | w26 | w27 | w28 | w29 | w30 | w31 | w32 | w33 | w34 | w35 | w36 | w37 | w38 | w39 | w40 | w41 | w42 | w43 | w44 | w45 | w46 | w47 | w48 | w49 | w50 | w51 | w52
Training Center constructions
Bidding document preparation and review | bar: Feb w7 to Feb w8
Bidding | bar: Mar w9 to Mar w11
Construction permit approval | bar: Mar w12 to Apr w15
Construction phase | bar: Apr w15 to Oct w43
Facilities insatllation | bar: Oct w41 to Nov w45
Building Finishing | bar: Nov w46 to Nov w48
Training Equipment order | bar: Aug w32 to Nov w44
Training Equipment installation | bar: Nov w45 to Nov w48
Furniture order | bar: Sep w39 to Nov w46
Funiture installation | bar: Nov w47 to Nov w48
Full funtional testing and handover | bar: Dec w49
Grand Opening | Dec w50: w50.1
Training centre Operations
Training Structure development | bar: May w18 to May w19
Develop a training content modules | bar: May w20 to Jun w26
Development Traing materials | bar: Jul w27 to Oct w43
Internal Basic training to employees
Train the Supervisor (32 days) | bar: Aug w31 to Sep w36
Train the Installer ( 10 days) | bar: Sep w37 to Sep w38
Train the Tester (11 day) | bar: Sep w37 to Sep w39
Train the Managers (40 days) | bar: Oct w40 to Dec w52
External practinoner and new KVI employee | bar: Dec w50 to Dec w52